## 17-239
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process | Note
Requirement analyze | 10 | Pham Minh Thanh | 9 | Done |  | 10
Design Front-end | 5 | Pham Minh Thanh | 8 | Done |  | 5
Design database | 5 | Pham Minh Thanh | 4 | Done |  | 5
Learning ASP.Net MVC5 | 20 | Pham Minh Thanh | 20 | Done |  | 18
Learning Entity Framework | 5 | Pham Minh Thanh | 4 | Done |  | 5
Load All House in District | 3 | Pham Minh Thanh | 4 | Done |  | 3
Pagination | 3 | Pham Minh Thanh | 5 | Done |  | 3
Show house details | 3 | Pham Minh Thanh | 2 | Done |  | 3
Total | 54 |  | 110.2% |  | Done task: | 96.3%
Requirement analyze | 12 | Duong Duc Duy | 12 | Done |  | 12
Design Front-end | 20 | Duong Duc Duy | 22 | Done |  | 20
Learning bootstrap | 5 | Duong Duc Duy | 4 | Done |  | 5
Stored Procedures | 5 | Duong Duc Duy | 5 | Done |  | 5
Learning ASP.Net MVC5 | 5 | Duong Duc Duy | 6 | Done |  | 5
Load All District | 3 | Duong Duc Duy | 4 | Done |  | 3
Search house by price or address | 10 | Duong Duc Duy | 9 | None |  | 10
Total | 60 |  | 122.4% |  | Done task: | 100%